## Project Planner
| Project Planner |  |  | 2-wheel self balancing robot
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 53 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Person | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
[7 empty] | 16/7 | 17/7 | [9 empty] | 27/7 |  |  |  |  | 2017-01-08 |  |  |  |  | 2017-06-08 | [6 empty] | 13/8 | [6 empty] | 20/8 | [6 empty] | 27/8 | [13 empty] | 14/9
ALL | Discuss Plan | 1 | 1 | 1 | 1 | 100%
Tung | Learn Tiva + Code library | 2 | 10 | 2 | 1
Hop | Learn Tiva + Code library | 2 | 10 | 2 | 1 | 90%
Nguyen | Learn Tiva + Code library | 2 | 10 | 2 | 10 | 90%
Nguyen | MPU6050 + Filter (Kalman, Complimentary) | 12 | 11 | 12 | 27 | 100%
Hop | H bridge + PID control | 12 | 11 |  |  | 90%
Tung | Hardware | 12 | 11 | 34 | 6 | 100%
Tung | Bluetooth Communication | 12 | 11
Hop | Solidworks | 23 | 7 |  |  | 100%
Nguyen + Tung | Android | 23 | 7 | 39 | 14 | 100%
ALL | Robot Assembly | 30 | 7 |  |  | 50%
Tung | Merge Code | 30 | 7
ALL | Test robot | 37 | 7
ALL | Fix robot | 37 | 20
ALL | Take photo of progress | 1 | 57
ALL | Race contest | 57 | 1

## Sheet1
| Start Date | Duration | End Date
Discuss Plant | 16/7/2017 | 1 | 16/7/2017
Learn Tiva + Code library | 17/7/2017 | 10 | 26/7/2017
MPU6050 + Filter (Kalman, Complimentary) | 27/7/2017 | 11 | 2017-08-06
H bridge + PID control | 27/7/2017 | 11 | 2017-08-06
Power Circuit | 27/7/2017 | 11 | 2017-08-06
Bluetooth Communication | 27/7/2017 | 11 | 2017-08-06
Solidworks | 2017-08-07 | 7 | 2017-08-13
Android | 2017-08-07 | 7 | 2017-08-13
Robot Assembly | 2017-08-14 | 7 | 2017-08-20
Merge Code | 2017-08-14 | 7 | 2017-08-20
Test robot | 2017-08-21 | 7 | 2017-08-27
Fix robot | 2017-08-21 | 7 | 2017-08-27
Take photo of progress | 16/7/2017 | 43 | 2017-08-27